## Sheet1
| Web Pages | Operation | APIs (Methods) | Estimations
| Project Setup |  |  | 2
1 | Login page | LogIn | Login | 1
2 | Main Page | Layout (Header & Sidebar) |  | 2
|  | Dashboard | Order detail count | 3
|  |  | User count (this week) | 1
|  |  | Latest orders details | 1
|  |  | View single order details | 1
3 | User Management Page | Users Data | All Users information | 2
|  |  | Users info list | 1
|  |  | User profile view | 1
|  |  | Delete user | 1
4 | Category Management Page | Category Lists | Display all main category list | 2
|  |  | Add main category | 1
|  |  | Edit main category | 1
|  |  | Delete main category | 1
5 | Product Management Page | Sub Category List | Display all sub category list | 2
|  |  | Add sub category | 1
|  |  | Edit sub category | 1
|  |  | Delete sub category | 1
|  | Products List | Display all product list | 2
|  |  | Add product | 1
|  |  | Edit product | 1
|  |  | Delete product | 1
6 | Order Management Page | User Based Orders | Order details for particular user | 2
|  |  | Particular order view | 1
|  | All Orders | All orders information | 2
7 | Manage Notification Page | Notify Users | All users | 2
|  |  | Single user | 1
8 | Main Page | LogOut | Logout | 1
9 | Unit Testing/Bug Fixing |  |  | 5
10 | Buffer Time |  |  | 5
|  |  | Total | 50